## Sheet1
TASK | USER STORY | RATIONAL | RISK | ASSIGNED TO | STATUS | START DATE
SPIRNT 1
User Class, Mood Class |  |  | High | Cameron | Not complete | 2019-10-17
HomePage Activity |  |  | Medium | Nevil | Not complete | 2019-10-17
Add Mood Event (no photo/location) |  |  | High | Ramy | Not complete | 2019-10-17
View Mood Event |  |  | Low | Josh | Not complete | 2019-10-17
Edit Mood Event |  |  | Medium | Travis | Not complete | 2019-10-17
Delete Mood Event |  |  | High | Nevil | Not complete | 2019-10-17
View Mood History (chronological/filter) |  |  | Medium | Cameron | Not complete | 2019-10-17
SPRINT 2
Profile Activity |  |  | Medium | Nevil | Not complete | 2019-11-01
Following n Follower feature |  |  | Medium | Sandy/Nevil/Cameron | Not complete | 2019-11-01
View following recent mood (reverse chronological) |  |  | Low | Josh/Ramy | Not complete | 2019-11-01
SPRINT 3
Map Activity |  |  | Medium | Cameron | Not complete | 2019-11-01
Add optional location in ADD MOOD |  |  | Low | Ramy/Josh | Not complete | 2019-11-15
View My Mood Map |  |  | Medium | Travis/Nevil | Not complete | 2019-11-15
View Following Mood Map |  |  | Low | Nevil/Sandy/Cameron | Not complete | 2019-11-15