## Sheet1
Priority | User Story | So That… | Risk | Assigned To | Status | Start Date
Sprint 1
1 | I want a profile with unique user name | I have unique account track my moods | High | Nevil | Not complete | 2019-10-17
2 | I want to add a mood event to my mood history | I can keep track of my moods | High | Cameron | Not complete | 2019-10-17
3 | I want it edit a mood event | I can change details of mood event if entered incorrectly | High | Josh | Not complete | 2019-10-17
4 | I want to delete a mood event | I can choose what moods my followers see | High | Ramy | Not complete | 2019-10-17
5 | I want to view a given mood event | I can see all details of the same | Medium | Travis | Not complete | 2019-10-17
6 | I want to view my mood history list in sorted reverse chronological order | I can view my most recent moods first | High | Sandy | Not complete | 2019-10-17
7 | I want to follow another participant | I can view their most recent mood event | Medium | Cameron | Not complete | 2019-10-17
8 | I want to grant another participant to follow my recent mood | Other participants can view my most recent mood | Medium | Nevil | Not complete | 2019-10-17
Sprint 2
9 | I want consistent emoticons to distinguish the emotional states | I can easily distinguish mood by images | Low | Not Assigned | Not complete | 2019-11-01
10 | I was to filter my mood history list by emotional state | I can view when I was in a particular emotional state | Medium | Not Assigned | Not complete | 2019-11-01
11 | I want to express a reason for each mood event | I can explain the reason for my mood | Low | Not Assigned | Not complete | 2019-11-01
12 | I want to express a reason using photograph | I easily distinguish the reason for my mood | Low | Not Assigned | Not complete | 2019-11-01
13 | I want to specify the social situation | I my followers know my social situation | Low | Not Assigned | Not complete | 2019-11-01
14 | I want to view the most recent mood events of other participants I am granted to view | I can view the most recent mood of my following participants | High | Not Assigned | Not complete | 2019-11-01
Sprint 3
15 | I want to optional attach my current location to mood event | I can get the location of each mood event | High | Not Assigned | Not complete | 2019-11-10
16 | I want to see a map of the mood events | I can keep track of my mood in each location | Medium | Not Assigned | Not complete | 2019-11-10
17 | I want to see a map of the mood events of the participants I am following | I can keep track of my partcipants moods in each location | Medium | Not Assigned | Not complete | 2019-11-10