## Sheet1
TASK | RISK | ASSIGNED TO | STATUS | START DATE
SPIRNT 1
User Class, Mood Class | High | Cameron | Not complete | 2019-10-17
HomePage Activity | Medium | Nevil | Not complete | 2019-10-17
Add Mood Event (no photo/location) | High | Ramy | Not complete | 2019-10-17
View Mood Event | Low | Josh | Not complete | 2019-10-17
Edit Mood Event | Medium | Travis | Not complete | 2019-10-17
Delete Mood Event | High | Nevil | Not complete | 2019-10-17
View Mood History (chronological/filter) | Medium | Cameron | Not complete | 2019-10-17
SPRINT 2
Profile Activity | Medium | Nevil | Not complete | 2019-11-01
Following n Follower feature | Medium | Sandy/Nevil/Cameron | Not complete | 2019-11-01
View following recent mood (reverse chronological) | Low | Josh/Ramy | Not complete | 2019-11-01
SPRINT 3
Map Activity | Medium | Cameron | Not complete | 2019-11-01
Add optional location in ADD MOOD | Low | Ramy/Josh | Not complete | 2019-11-15
View My Mood Map | Medium | Travis/Nevil | Not complete | 2019-11-15
View Following Mood Map | Low | Nevil/Sandy/Cameron | Not complete | 2019-11-15